## Sheet
Well Name: |  | 463H
Rig: |  | Nabors X47
Operator: |  | Chevron U.S.A. Inc.
Job ID:
Report Date: |  | 2026-02-22T00:00:00
[6 empty] | Time (hrs) |  |  |  | Depth (ft)
Phase | Type | Activity | IADC Sub Code | Status | Description | Plan | Actual | Start Date | End Date | Start Plan | End Plan | Start Actual | End Actual
INTERMEDIATE | PLANNED | SKID RIG | 1.F |  | Skid Rig | 0.5 |  |  |  | 450 | 450
INTERMEDIATE | PLANNED | NIPPLE UP BOPS | 14.A |  | Nipple Up BOPS | 0.85 |  |  |  | 450 | 450
INTERMEDIATE | PLANNED | TEST BOPS | 15.A |  | Test BOPS | 0.91 |  |  |  | 450 | 450
INTERMEDIATE | PLANNED | INSTALL/REMOVE WEAR BUSHING | 6.K |  | Install Wear Bushing | 0.45 |  |  |  | 450 | 450
INTERMEDIATE | PLANNED | PICK UP BHA | 6.C |  | P/U 12.25" PDC w/ Phoenix 9in Atlas + Gordon MWD | 0.8 |  |  |  | 450 | 450
INTERMEDIATE | PLANNED | TRIP IN HOLE | 6.A |  | TIH | 3.57 |  |  |  | 450 | 450
INTERMEDIATE | PLANNED | CHANGE ROTATING HEAD/RUBBER | 14.F |  | Install Rot Head | 0.5 |  |  |  | 450 | 450
INTERMEDIATE | PLANNED | DRILLING CEMENT | 2.C |  | Drill Cement w/ 12.25" PDC | 0.49 |  |  |  | 450 | 450
INTERMEDIATE | PLANNED | ROTARY DRILLING | 2.A |  | Drill 10' of New Formation before FIT | 0.24 |  |  |  | 450 | 460
INTERMEDIATE | PLANNED | CIRCULATE AND CONDITION | 5.D |  | Circulate & Condition [8.5-9.5# WBM] | 0.5 |  |  |  | 460 | 460
INTERMEDIATE | PLANNED | FORMATION INTEGRITY TEST (FIT) | 12.I |  | Formation Integrity Test (FIT) | 0.48 |  |  |  | 460 | 460
INTERMEDIATE | PLANNED | ROTARY DRILLING | 2.A |  | Drill Int Section to TD | 28.98 |  |  |  | 460 | 8500
INTERMEDIATE | PLANNED | CIRCULATE AND CONDITION | 5.D |  | Circulate & Condition [8.5-9.5# WBM] | 1.36 |  |  |  | 8500 | 8500
INTERMEDIATE | PLANNED | FLOW CHECK | 23.B |  | Flow Check | 0.25 |  |  |  | 8500 | 8500
INTERMEDIATE | PLANNED | TRIP OUT OF HOLE | 6.B |  | TOOH T/Shoe | 2.12 |  |  |  | 8500 | 8500
INTERMEDIATE | PLANNED | CHANGE ROTATING HEAD/RUBBER | 14.F |  | Remove Rot Head | 0.5 |  |  |  | 8500 | 8500
INTERMEDIATE | PLANNED | TRIP OUT OF HOLE | 6.B |  | TOOH to Surface | 1.01 |  |  |  | 8500 | 8500
INTERMEDIATE | PLANNED | PRE JOB SAFETY | 22.D |  | PJSM for BHA | 0.25 |  |  |  | 8500 | 8500
INTERMEDIATE | PLANNED | LAY DOWN BHA | 6.D |  | Lay Down BHA | 0.91 |  |  |  | 8500 | 8500
INTERMEDIATE | PLANNED | INSTALL/REMOVE WEAR BUSHING | 6.K |  | Remove Wear Bushing | 0.45 |  |  |  | 8500 | 8500
INTERMEDIATE | PLANNED | PRE JOB SAFETY | 22.D |  | PJSM for R/U Casing Crew & Running Casing | 0.45 |  |  |  | 8500 | 8500
INTERMEDIATE | PLANNED | RIG UP/DOWN TO RUN CASING | 12.A |  | R/U Casing Crew | 0.66 |  |  |  | 8500 | 8500
INTERMEDIATE | PLANNED | RUN CASING | 12.B |  | Run 7.625" Casing | 16.02 |  |  |  | 8500 | 8500
INTERMEDIATE | PLANNED | CIRCULATE AND CONDITION | 5.D |  | Circulate & Condition [8.5-9.5# WBM] | 1.23 |  |  |  | 8500 | 8500
INTERMEDIATE | PLANNED | RIG UP/DOWN TO RUN CASING | 12.A |  | R/D Casing Crew | 0.5 |  |  |  | 8500 | 8500
INTERMEDIATE | PLANNED | INSTALL WELLHEADS | 14.I |  | Install Wellheads | 0.45 |  |  |  | 8500 | 8500
INTERMEDIATE | PLANNED | NIPPLE DOWN BOPS | 14.B |  | Nipple Down BOPS | 0.5 |  |  |  | 8500 | 8500
PRODUCTION | PLANNED | SKID RIG | 1.F |  | Skid Rig | 0.75 |  |  |  | 9000 | 9000
PRODUCTION | PLANNED | NIPPLE UP BOPS | 14.A |  | Nipple Up BOPS | 0.88 |  |  |  | 9000 | 9000
PRODUCTION | PLANNED | TEST BOPS | 15.A |  | Test BOPS | 3.68 |  |  |  | 9000 | 9000
PRODUCTION | PLANNED | INSTALL/REMOVE WEAR BUSHING | 6.K |  | Install Wear Bushing | 0.5 |  |  |  | 9000 | 9000
PRODUCTION | PLANNED | PRE JOB SAFETY | 22.D |  | Pre Job Safety Meeting | 0.44 |  |  |  | 9000 | 9000
PRODUCTION | PLANNED | PICK UP BHA | 6.C |  | P/U 6.75" PDC w/ Phoenix 5.75in Atlas + Gordon MWD | 0.99 |  |  |  | 9000 | 9000
PRODUCTION | PLANNED | TRIP IN HOLE | 6.A |  | TIH | 2.5 |  |  |  | 9000 | 9000
PRODUCTION | PLANNED | CHANGE ROTATING HEAD/RUBBER | 14.F |  | Install Rot Head | 0.48 |  |  |  | 9000 | 9000
PRODUCTION | PLANNED | DRILLING CEMENT | 2.C |  | Drill Cement w/ 6.75" PDC | 1.36 |  |  |  | 9000 | 9000
PRODUCTION | PLANNED | ROTARY DRILLING | 2.A |  | Drill 10' into TB1C INT2 Casing Window Base before FIT | 0.25 |  |  |  | 9000 | 9010
PRODUCTION | PLANNED | CIRCULATE AND CONDITION | 5.D |  | Circulate & Condition [10.1-11.2# OBM] | 0.45 |  |  |  | 9010 | 9010
PRODUCTION | PLANNED | FORMATION INTEGRITY TEST (FIT) | 12.I |  | FIT @ TB1C INT2 Casing Window Base (~8,521.3' MD) | 0.5 |  |  |  | 9010 | 9010
PRODUCTION | PLANNED | SLIDE DRILLING | 2.B |  | Build 6.75" Curve to LP @ 9,000' (TB1C thru Wolfcamp A1 (WCA1)) [10.1-11.2# OBM] | 6 |  |  |  | 9010 | 9000
PRODUCTION | PLANNED | CIRCULATE AND CONDITION | 5.D |  | Circulate & Condition [10.1-11.2# OBM] | 1.49 |  |  |  | 9000 | 9000
PRODUCTION | PLANNED | FLOW CHECK | 23.B |  | Flow Check | 0.25 |  |  |  | 9000 | 9000
PRODUCTION | PLANNED | TRIP OUT OF HOLE | 6.B |  | TOOH to 5.0" Shoe @ 19,254.5' | 2.34 |  |  |  | 9000 | 9000
PRODUCTION | PLANNED | CHANGE ROTATING HEAD/RUBBER | 14.F |  | Remove Rot Head | 0.44 |  |  |  | 9000 | 9000
PRODUCTION | PLANNED | TRIP OUT OF HOLE | 6.B |  | TOOH to Surface | 2.33 |  |  |  | 9000 | 9000
PRODUCTION | PLANNED | PRE JOB SAFETY | 22.D |  | PJSM for BHA | 0.25 |  |  |  | 9000 | 9000
PRODUCTION | PLANNED | LAY DOWN BHA | 6.D |  | Lay Down BHA | 0.72 |  |  |  | 9000 | 9000
PRODUCTION | PLANNED | PICK UP BHA | 6.C |  | P/U 6.75" PDC w/ Phoenix 5.75in Atlas + Gordon MWD | 1.25 |  |  |  | 9000 | 9000
PRODUCTION | PLANNED | TRIP IN HOLE | 6.A |  | TIH | 5.02 |  |  |  | 9000 | 9000
PRODUCTION | PLANNED | CHANGE ROTATING HEAD/RUBBER | 14.F |  | Install Rot Head | 0.48 |  |  |  | 9000 | 9000
PRODUCTION | PLANNED | ROTARY DRILLING | 2.A |  | Drill 6.75" Lateral in Wolfcamp A to TD @ 19,254.5' [10.1-11.2# OBM] | 59.91 |  |  |  | 9000 | 19254.48
PRODUCTION | PLANNED | TRIP OUT OF HOLE | 6.B |  | TOOH to 5.0" Shoe @ 19,254.5' | 8.2 |  |  |  | 19254.48 | 19254.48
PRODUCTION | PLANNED | CHANGE ROTATING HEAD/RUBBER | 14.F |  | Remove Rot Head | 1 |  |  |  | 19254.48 | 19254.48
PRODUCTION | PLANNED | TRIP OUT OF HOLE | 6.B |  | TOOH to Surface | 5.2 |  |  |  | 19254.48 | 19254.48
PRODUCTION | PLANNED | PRE JOB SAFETY | 22.D |  | PJSM for BHA | 0.25 |  |  |  | 19254.48 | 19254.48
PRODUCTION | PLANNED | LAY DOWN BHA | 6.D |  | Lay Down BHA | 1.25 |  |  |  | 19254.48 | 19254.48
PRODUCTION | PLANNED | INSTALL/REMOVE WEAR BUSHING | 6.K |  | Remove Wear Bushing | 0.51 |  |  |  | 19254.48 | 19254.48
PRODUCTION | PLANNED | PRE JOB SAFETY | 22.D |  | PJSM for R/U Casing Crew & Running Casing | 0.43 |  |  |  | 19254.48 | 19254.48
PRODUCTION | PLANNED | RIG UP/DOWN TO RUN CASING | 12.A |  | R/U Casing Crew | 0.95 |  |  |  | 19254.48 | 19254.48
PRODUCTION | PLANNED | RUN CASING | 12.B |  | Run 5.0" 13.0# Prod Csg to 19,254.5' | 27.46 |  |  |  | 19254.48 | 19254.48
PRODUCTION | PLANNED | CIRCULATE AND CONDITION | 5.D |  | Circulate & Condition [10.1-11.2# OBM] | 2.52 |  |  |  | 19254.48 | 19254.48
PRODUCTION | PLANNED | RIG UP/DOWN TO RUN CASING | 12.A |  | R/D Casing Crew | 0.53 |  |  |  | 19254.48 | 19254.48
PRODUCTION | PLANNED | PRIMARY CEMENTING | 12.C |  | Primary Cement (offline) | 6.3 |  |  |  | 19254.48 | 19254.48
PRODUCTION | PLANNED | NIPPLE DOWN BOPS | 14.B |  | Nipple Down BOPS | 0.5 |  |  |  | 19254.48 | 19254.48